## Schedule
Needed | Responsible | Due Date |  |  |  | Observation
|  | February | March | April | May
UI
Home page (Design) | Sarah/Ines | 2016-02-13 |  |  |  | Done
Menu | Sarah/Ines | 2016-02-13 |  |  |  | Done
Links menu to pages | Sarah/Ines | 2016-02-13 |  |  |  | Done | RemarK
Pop up Info Map (Design) | Sarah/Ines | 2016-02-13 |  |  |  | Done |  | 1st week
Search bar Map (Design) | Sarah/Ines | 2016-02-13 |  |  |  | Done |  | 2nd week
Detailed search Menu | Sarah/Ines | 2016-02-20 |  |  |  | Done |  | 3rd week
Create Design | Sarah/Ines | 2016-02-20 |  |  |  | Done |  | 4th week
Integrate Map | Sarah/Ines | 2016-02-20 |  |  |  | Done
Clickable objects in Map | Sarah/Ines | 20 -? /02/2016 |  |  |  | Done
Camera Slide on Click/touch | Sarah/Ines | 2016-02-20 |  |  |  | Done
Side Menu | Sarah/Ines | 2016-02-20 |  |  |  | Done
Functionality Search Bar Map | Ines/Samer | 2016-02-27 |  |  |  | Done
Pop up -->Database | Ines/Sarah | 2016-02-27 |  |  |  | Done
List Info --> Databse | Ines/Sarah |  | 2016-03-06 |  |  | Done
Finish UI 'on campus' | Sarah/Ines |  | 2016-03-12 |  |  | Done
Finish Linking Database | Sarah/Ines |  | 2016-03-12 |  |  | Done
Finish UI 'on campus' | Sarah/Ines |  | 2016-03-26 |  |  | Done
Finish Linking Database | Sarah/Ines |  | 2016-03-26 |  |  | Done
Adding Details | Sarah/Ines |  | April end |  |  | In progress
Camera Navigation | Samer |  | April end |  |  | Done
Buildings
President's house | Samer | 2016-02-20 |  |  |  | Done
Cafeteria | Samer | 2016-02-20 |  |  |  | Done
Maingate | Samer | 2016-02-20 |  |  |  | Done
College hall | Samer | 2016-02-20 |  |  |  | Done
Jafet | Samer | 2016-02-20 |  |  |  | Done
Assembly hall | Sarah | 2016-02-27 |  |  |  | Done
Post Hall | Sarah | 2016-02-27 |  |  |  | Done
Van Dyck | Sarah | 2016-02-27 |  |  |  | Done
Medical building | Sarah | 2016-02-27 |  |  |  | Done
Old pharmacy | Sarah | 2016-02-27 |  |  |  | Done
Medical gate | Samer | 2016-02-27 |  |  |  | Done
OXY | Ines |  | 2016-03-06 |  |  | Done
OSB | Ines |  | 2016-03-06 |  |  | Done
Gym | Ines |  | 2016-03-12 |  |  | Done
Levels | All |  | 2016-03-12 |  |  | In Progress
Maingate observatory penrose gate | Samer |  | 2016-03-26 |  |  | Done
Terrain(bliss west) Vandyk | Sarah |  | 2016-03-26 |  |  | Done
SRB, medical building | Ines |  | 2016-03-26 |  |  | Done
Archi Bechtel RGB REP | Sarah |  | 2016-04-04 |  |  | Done
Dorms,Chimestry, Prebuild | Ines |  | 2016-04-04 |  |  | Done
Physics Agri Bio | Samer |  | 2016-04-04 |  |  | Done
Data
Data Base Design | Ines | 2016-02-13 |  |  |  | Done
Classes/Teachers/Departmnets/Buildings/Faculties | Ines | 2016-02-13 |  |  |  | Done
Create Data Base | Ines | 2016-02-13 |  |  |  | Done
Populate Data Base | Ines | 2016-02-13 |  |  |  | Done
Eat/Study/Discover(on campus) | Ines | 2016-02-20 |  |  |  | Done
Building description | Ines | 2016-02-20 |  |  |  | Done
Machine/Paper work | Ines | 2016-02-20 |  |  |  | Done
pictures on campus | Ines | 2016-02-20 |  |  |  | Done
Get pictures (On-Off Campus) | Samer | 2016-02-27 |  |  |  | Done
Eating/Discover/Study Places (off campus) | Samer | 2016-02-27 |  |  |  | Done
Special Places(more data) | Samer |  | 2016-03-06 |  |  | Done
Interesting Places Information | Samer |  | 2016-03-06 |  |  | In Progress
Discover Off campus | Sarah |  | 2016-03-12 |  |  | In Progress
Info campus | Ines |  | 2016-03-12 |  |  | Done
Finish parsing database | Samer |  | 2016-03-12 |  |  | Done
Add Table Classes | Sarah/Ines |  | 2016-03-26 |  |  | Done
Add Table Buildings Coordinates | Sarah/Ines |  | 2016-03-26 |  |  | Done